## Model
Room construction project
Data on activity network |  |  |  | Parameters of PERT distributions
Activity | Code | Numeric index | Predecessors | Min | Most likely | Max | Implied mean | Duration | Duration+
Prepare foundation | A | 1 | None | 1.5 | 3.5 | 8.5 | 4 | 4 | 4.001
Put up frame | B | 2 | A | 3 | 4 | 5 | 4 | 4 | 4
Order custom windows | C | 3 | None | 7 | 10 | 19 | 11 | 11 | 11
Erect outside walls | D | 4 | B | 2 | 2.5 | 6 | 3 | 3 | 3
Do electrical wiring | E | 5 | D | 3 | 3.5 | 7 | 4 | 4 | 4
Do plumbing | F | 6 | D | 2 | 2.5 | 6 | 3 | 3 | 3
Put in duct work | G | 7 | D | 2 | 4 | 6 | 4 | 4 | 4
Hang dry wall | H | 8 | E,F,G | 2.5 | 3 | 3.5 | 3 | 3 | 3
Install windows | I | 9 | B,C | 0.5 | 1 | 1.5 | 1 | 1 | 1
Paint and clean up | J | 10 | H | 1.5 | 2 | 2.5 | 2 | 2 | 2
Index of activity to increase | 1
Event times
Node | Event time | Event time+
1 | 0 | 0
2 | 4 | 4.001
3 | 8 | 8.001
4 | 11 | 11
5 | 11 | 11.001
6 | 15 | 15.001
7 | 18 | 18.001
8 | 20 | 20.001
Increase in project time? | 1